## CPM Schedule
CRITICAL PATH METHOD SCHEDULE
3610 E Dr Martin Luther King Jr Blvd, Tampa, FL 33610 ¦ Lionize Construction ¦ Contract No. 25-P-00039
Project Start: 06/15/2025 ¦ Project End: 08/14/2025 ¦ 60 Calendar Days ¦ Workdays: Mon–Sat (Sundays Excluded) |  |  |  |  | ■ Critical ■ Non-Crit ◆ Rough Insp ◆ Final Insp ★ Milestone
# | Task / Work Item | Assigned To | Phase / Category | Dur (Days) | Early Start | Early Finish | Late Start | Late Finish | Float
1 | Soffit & Fascia | Orange Painting Services | Critical Path | 5 | 06/15/2025 | 06/20/2025 | 06/19/2025 | 06/25/2025 | 4
2 | Roofing & Gutters | Sunny R&R LLC | Critical Path | 5 | 06/19/2025 | 06/25/2025 | 06/24/2025 | 06/30/2025 | 4
3 | Remove Ceiling & Insulation | Gruntle, LLC | Critical Path | 4 | 06/25/2025 | 06/30/2025 | 06/30/2025 | 07/04/2025 | 4
4 | Rough Electrical | 104 Electrical | Critical Path | 4 | 06/30/2025 | 07/04/2025 | 07/01/2025 | 07/05/2025 | 1
5 | HVAC Rough-In / Ductwork | Authentic Air Solutions LLC | Non-Critical | 4 | 06/30/2025 | 07/04/2025 | 07/01/2025 | 07/05/2025 | 1
6 | Rough Electrical Inspection | City of Tampa Bldg Dept | Rough Inspection | 1 | 07/04/2025 | 07/05/2025 | 07/07/2025 | 07/08/2025 | 2
7 | Rough HVAC Inspection | City of Tampa Bldg Dept | Rough Inspection | 1 | 07/04/2025 | 07/05/2025 | 07/07/2025 | 07/08/2025 | 2
8 | Spray Insulation | Gruntle, LLC | Critical Path | 2 | 07/05/2025 | 07/08/2025 | 07/15/2025 | 07/17/2025 | 8
9 | Install New Ceiling | Gruntle, LLC | Critical Path | 8 | 07/08/2025 | 07/17/2025 | 07/10/2025 | 07/19/2025 | 2
10 | Windows Installation | Gruntle, LLC | Non-Critical | 3 | 07/17/2025 | 07/21/2025 | 08/11/2025 | 08/14/2025 | 21
11 | Electrical Trim-Out / Devices | 104 Electrical | Critical Path | 2 | 07/17/2025 | 07/19/2025 | 07/31/2025 | 08/02/2025 | 12
12 | HVAC Trim-Out / Equipment | Authentic Air Solutions LLC | Non-Critical | 2 | 07/17/2025 | 07/19/2025 | 08/11/2025 | 08/13/2025 | 21
13 | Flooring Removal and Installation | Orange Painting Services | Critical Path | 12 | 07/19/2025 | 08/02/2025 | 07/21/2025 | 08/04/2025 | 1
14 | Toilet Replacement | Gruntle, LLC | Non-Critical | 1 | 08/02/2025 | 08/04/2025 | 08/11/2025 | 08/12/2025 | 7
15 | Exterior Painting | Orange Painting Services | Critical Path | 3 | 08/02/2025 | 08/06/2025 | 08/05/2025 | 08/08/2025 | 2
16 | Termites Tent / Subterraneal Pest Treatment | Termites | Critical Path | 2 | 08/06/2025 | 08/08/2025 | 08/09/2025 | 08/12/2025 | 3
17 | Cleaning | W. Endless Solutions | Critical Path | 3 | 08/08/2025 | 08/12/2025 | 08/09/2025 | 08/13/2025 | 1
18 | Electrical Final Inspection | City of Tampa Bldg Dept | Final Inspection | 1 | 08/12/2025 | 08/13/2025 | 08/13/2025 | 08/14/2025 | 1
19 | HVAC Final Inspection | City of Tampa Bldg Dept | Final Inspection | 1 | 08/12/2025 | 08/13/2025 | 08/13/2025 | 08/14/2025 | 1
20 | City of Tampa Final Building Inspection | City of Tampa Bldg Dept | Milestone / CO | 1 | 08/13/2025 | 08/14/2025 | 08/13/2025 | 08/14/2025 | 0
PROJECT TOTALS |  |  |  | 65

## Gantt Chart
GANTT CHART – 3610 E Dr Martin Luther King Jr Blvd, Tampa, FL 33610
Lionize Construction ¦ Contract 25-P-00039 ¦ 06/15/2025 – 08/14/2025 ¦ Mon–Sat (Sundays Excluded)
[6 empty] | June 2025 |  |  |  | July 2025 |  |  |  | August 2025
# | Task / Work Item | Assigned To | Dur (Days) | Start | End | 6/9 | 6/16 | 6/23 | 6/30 | 7/7 | 7/14 | 7/21 | 7/28 | 8/4 | 8/11 | 8/18
1 | Soffit & Fascia | Orange Painting Services | 5 | 06/15/2025 | 06/20/2025 | Soffit & Fascia
2 | Roofing & Gutters | Sunny R&R LLC | 5 | 06/19/2025 | 06/25/2025 |  | Roofing & Gutters
3 | Remove Ceiling & Insulation | Gruntle, LLC | 4 | 06/25/2025 | 06/30/2025 |  |  | Remove Ceiling & Insulatio
4 | Rough Electrical | 104 Electrical | 4 | 06/30/2025 | 07/04/2025 |  |  |  | Rough Electrical
5 | HVAC Rough-In / Ductwork | Authentic Air Solutions LLC | 4 | 06/30/2025 | 07/04/2025 |  |  |  | HVAC Rough-In / Ductwork
6 | Rough Electrical Inspection | City of Tampa Bldg Dept | 1 | 07/04/2025 | 07/05/2025 |  |  |  | Rough Electrical Inspectio
7 | Rough HVAC Inspection | City of Tampa Bldg Dept | 1 | 07/04/2025 | 07/05/2025 |  |  |  | Rough HVAC Inspection
8 | Spray Insulation | Gruntle, LLC | 2 | 07/05/2025 | 07/08/2025 |  |  |  | Spray Insulation
9 | Install New Ceiling | Gruntle, LLC | 8 | 07/08/2025 | 07/17/2025 |  |  |  |  | Install New Ceiling
10 | Windows Installation | Gruntle, LLC | 3 | 07/17/2025 | 07/21/2025 | [5 empty] | Windows Installation
11 | Electrical Trim-Out / Devices | 104 Electrical | 2 | 07/17/2025 | 07/19/2025 | [5 empty] | Electrical Trim-Out / Devi
12 | HVAC Trim-Out / Equipment | Authentic Air Solutions LLC | 2 | 07/17/2025 | 07/19/2025 | [5 empty] | HVAC Trim-Out / Equipment
13 | Flooring Removal and Installation | Orange Painting Services | 12 | 07/19/2025 | 08/02/2025 | [5 empty] | Flooring Removal and Insta
14 | Toilet Replacement | Gruntle, LLC | 1 | 08/02/2025 | 08/04/2025 | [7 empty] | Toilet Replacement
15 | Exterior Painting | Orange Painting Services | 3 | 08/02/2025 | 08/06/2025 | [7 empty] | Exterior Painting
16 | Termites Tent / Subterraneal Pest Treatment | Termites | 2 | 08/06/2025 | 08/08/2025 | [8 empty] | Termites Tent / Subterrane
17 | Cleaning | W. Endless Solutions | 3 | 08/08/2025 | 08/12/2025 | [8 empty] | Cleaning
18 | Electrical Final Inspection | City of Tampa Bldg Dept | 1 | 08/12/2025 | 08/13/2025 | [9 empty] | Electrical Final Inspectio
19 | HVAC Final Inspection | City of Tampa Bldg Dept | 1 | 08/12/2025 | 08/13/2025 | [9 empty] | HVAC Final Inspection
20 | City of Tampa Final Building Inspection | City of Tampa Bldg Dept | 1 | 08/13/2025 | 08/14/2025 | [9 empty] | City of Tampa Final Buildi
■ Critical Path | ■ Non-Critical | ◆ Rough Insp | ◆ Final Insp | ★ Milestone | Mon–Sat ¦ No Sundays

## CPM Summary
CPM NETWORK ANALYSIS – CRITICAL PATH SUMMARY
3610 E Dr Martin Luther King Jr Blvd ¦ Lionize Construction ¦ Contract 25-P-00039
Project Start Date |  | 06/15/2025
Project End Date |  | 08/14/2025
Calendar Duration |  | 60 calendar days
Workday Calendar |  | Monday – Saturday (Sundays Excluded)
Roofing Start Date |  | 06/19/2025 (per owner direction)
Total Tasks |  | 20
Critical Path Tasks |  | 11
Inspection Milestones |  | 5
Non-Critical Tasks |  | 4
PROJECT PHASES & CRITICAL PATH
PHASE 1 – ENVELOPE
1 | Soffit & Fascia |  | Orange Painting Services | 5d | 06/15 – 06/20/2025
2 | Roofing & Gutters |  | Sunny R&R LLC | 5d | 06/19 – 06/25/2025
PHASE 2 – DEMO
3 | Remove Ceiling & Insulation |  | Gruntle, LLC | 4d | 06/25 – 06/30/2025
PHASE 3 – ROUGH-IN
4 | Rough Electrical |  | 104 Electrical | 4d | 06/30 – 07/04/2025
5 | HVAC Rough-In / Ductwork |  | Authentic Air Solutions LLC | 4d | 06/30 – 07/04/2025
PHASE 4 – INSPECTIONS (ROUGH)
6 | Rough Electrical Inspection |  | City of Tampa Bldg Dept | 1d | 07/04 – 07/05/2025
7 | Rough HVAC Inspection |  | City of Tampa Bldg Dept | 1d | 07/04 – 07/05/2025
PHASE 5 – INSULATION & CLOSE
8 | Spray Insulation |  | Gruntle, LLC | 2d | 07/05 – 07/08/2025
9 | Install New Ceiling |  | Gruntle, LLC | 8d | 07/08 – 07/17/2025
PHASE 6 – TRIM-OUT & WINDOWS
10 | Windows Installation |  | Gruntle, LLC | 3d | 07/17 – 07/21/2025
11 | Electrical Trim-Out / Devices |  | 104 Electrical | 2d | 07/17 – 07/19/2025
12 | HVAC Trim-Out / Equipment |  | Authentic Air Solutions LLC | 2d | 07/17 – 07/19/2025
PHASE 7 – FINISHES
13 | Flooring Removal and Installation |  | Orange Painting Services | 12d | 07/19 – 08/02/2025
14 | Toilet Replacement |  | Gruntle, LLC | 1d | 08/02 – 08/04/2025
15 | Exterior Painting |  | Orange Painting Services | 3d | 08/02 – 08/06/2025
PHASE 8 – TERMITES & CLEAN
16 | Termites Tent / Subterraneal Pest Treatment |  | Termites | 2d | 08/06 – 08/08/2025
17 | Cleaning |  | W. Endless Solutions | 3d | 08/08 – 08/12/2025
PHASE 9 – INSPECTIONS (FINAL)
18 | Electrical Final Inspection |  | City of Tampa Bldg Dept | 1d | 08/12 – 08/13/2025
19 | HVAC Final Inspection |  | City of Tampa Bldg Dept | 1d | 08/12 – 08/13/2025
20 | City of Tampa Final Building Inspection |  | City of Tampa Bldg Dept | 1d | 08/13 – 08/14/2025